## Risk Dashboard
MEDCLOUD SOLUTIONS
Information Security Risk Dashboard
Metric | Value | Risk Level | Count
Total Risks |  | Critical
Critical Risks |  | High
High Risks |  | Medium
Medium Risks |  | Low
Low Risks
Open Risks
Company | MedCloud Solutions
Industry | Healthcare SaaS
Employees | 80
Assessment Type | Mock GRC Risk Assessment
Assessment Date | 2026-08-20

## Risk Register
Risk ID | Risk Description | Asset | Threat | Vulnerability | Likelihood (1-5) | Impact (1-5) | Risk Score | Risk Level | Risk Treatment | Control / Mitigation | Risk Owner | Target Date | Status
R-001 | Unauthorized access to patient records | Patient Database | Credential theft | MFA not enforced for all privileged/remote accounts | 4 | 5 |  |  | Mitigate | Enforce MFA and review privileged access monthly | IT Manager | 2026-09-20 | Open
R-002 | Ransomware could disrupt services and cause data loss | Production Systems | Ransomware | Backups are not regularly restore-tested | 3 | 5 |  |  | Mitigate | Implement immutable backups and quarterly restore tests | IT Manager | 2026-10-05 | Open
R-003 | Phishing could compromise employee accounts | Microsoft 365 Accounts | Phishing | Limited security awareness training and simulations | 4 | 4 |  |  | Mitigate | Conduct annual training and quarterly phishing simulations | Security Manager | 2026-09-15 | Open
R-004 | Backup failure could prevent recovery after an incident | Backup Repository | Hardware/software failure | No documented recovery testing evidence | 3 | 5 |  |  | Mitigate | Document backup ownership and perform quarterly recovery tests | Infrastructure Lead | 2026-10-10 | Open
R-005 | Excessive privileges could enable unauthorized data access | IAM | Privilege abuse | Access reviews are not performed consistently | 4 | 4 |  |  | Mitigate | Implement RBAC and quarterly user access reviews | IAM Administrator | 2026-09-30 | Open
R-006 | Cloud misconfiguration could expose sensitive data | Cloud Storage | Misconfiguration | Configuration reviews and monitoring are incomplete | 3 | 5 |  |  | Mitigate | Enable configuration monitoring and periodic security reviews | Cloud Administrator | 2026-10-01 | Open
R-007 | Third-party vendor breach could expose company data | Vendor Services | Supply-chain compromise | Vendor security assessments are informal | 3 | 4 |  |  | Mitigate | Introduce vendor due diligence and annual reassessment | Compliance Manager | 2026-10-15 | Open
R-008 | Insider data leakage could expose confidential information | Patient Records | Insider threat | Data access monitoring is limited | 2 | 5 |  |  | Mitigate | Apply least privilege and monitor sensitive-data access | Security Manager | 2026-10-20 | Open
R-009 | Unpatched systems could be exploited | Endpoints/Servers | Exploitation | Patch management SLA is not consistently enforced | 4 | 4 |  |  | Mitigate | Define patch SLAs and track exceptions | Infrastructure Lead | 2026-09-25 | Open
R-010 | Lost employee laptop could expose company information | Employee Laptop | Device loss/theft | Encryption and remote-wipe coverage may be incomplete | 3 | 3 |  |  | Mitigate | Enforce full-disk encryption and MDM remote wipe | IT Manager | 2026-09-30 | Open
R-011 | Weak incident response could increase business impact | Incident Response Process | Security incident | Playbook has not been tested through a tabletop exercise | 3 | 4 |  |  | Mitigate | Conduct a tabletop exercise and update the playbook | Security Manager | 2026-10-25 | Open
R-012 | Poor employee offboarding could leave accounts active | User Accounts | Account misuse | Joiner/mover/leaver process is not fully documented | 3 | 4 |  |  | Mitigate | Formalize offboarding checklist and disable accounts promptly | HR Manager | 2026-09-20 | Open

## Risk Matrix
MedCloud Solutions — 5×5 Risk Matrix
Likelihood ↓ / Impact → | 1 | 2 | 3 | 4 | 5
5 | 5 | 10 | 15 | 20 | 25
4 | 4 | 8 | 12 | 16 | 20
3 | 3 | 6 | 9 | 12 | 15
2 | 2 | 4 | 6 | 8 | 10
1 | 1 | 2 | 3 | 4 | 5
Score | Level | Action
1–4 | Low | Monitor / minor improvement
5–9 | Medium | Planned remediation
10–15 | High | Prioritized remediation
16–25 | Critical | Immediate management attention